## PhoneDo
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
Manage own account | Authorization | As BA on the onboarding steps I can add Simple script and FAQ |  | Todo | 16.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Lawyer Jack
Manage own account | Authorization | As BA I can signup on the web (onboarding screens+apology page) |  | Todo | 36.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage own account | Authorization | As BA I can signup entering my phone number, getting SMS code and setting password (Ran's UI) |  | Todo | 20.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage own account | Authorization | As BA I can sign in and sign out (Ran's UI) |  | Todo | 8.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage own account | Manage business account details and settings | As BA I can switch interface language |  | Todo | 16.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage own account | Manage business account details and settings | As BA I can setup Google calendar integration |  | Todo | 40.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage own account | Manage business account details and settings | As BA I can select which google calendar to use and unlink calendar |  | Todo | 12.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage own account | Manage business account details and settings | Option to add main company details | Country (where operates) Address Industry Departments Telephone numbers | Todo | 6.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Lawyer Jack
Manage scripts | Add script | As BA I can add a script of type Survey with set or free answers | Survey is a type of script with an option to add many questions and add possible answers. | Todo | 30.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage scripts | Add script | Open the section with and view the list of own scripts (grid) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Lawyer Jack
Manage scripts | Add script | Add new script. for himself Fields: Title, Text (basic version for now) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Lawyer Jack
Manage scripts | Update script | As BA I can set the priority for Scripts |  | Todo | 4.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Lawyer Jack
Manage scripts | Update script | Open an existing script and change Title, text |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Lawyer Jack
Manage modules | Add and update modules | As BA I can view Events cards (section) |  | Todo | 10.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage modules | Add and update modules | As BA I can add new Events and enable/disable registration for it |  | Todo | 28.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage modules | Add and update modules | As BA I can view Media section |  | Todo | 12.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage modules | Add and update modules | As BA I can add and remove Media items (PDF, JPEG, GIF files) |  | Todo | 24.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage modules | Add and update modules | As BA I visit Stuff members section and view grid with members |  | Todo | 16.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage modules | Add and update modules | As BA I can add a new Stuff member and update it in future |  | Todo | 20.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage modules | Add and update modules | As BA I visit Places section and view grid with Places |  | Todo | 12.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage modules | Add and update modules | As BA I can add a new Place and update it in future |  | Todo | 12.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage modules | Add and update modules | As BA I can start typing a place name and use autosuggested fields (Google Places API) |  | Todo | 16.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage modules | Add and update modules | As BA I can add FAQ items for hotline |  | Todo | 16.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage modules | Add and update modules | As BA I can visit Products Catalogue section and view a grid with products |  | Todo | 16.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage modules | Add and update modules | As BA I can add a new product and update it in future |  | Todo | 20.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage modules | Add and update modules | As BA I can add translations for products |  | Todo | 10.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage hotline | Setup hotline | Option to select the prefix for the number |  | Todo |  | Unscheduled | Lawyer Jack
Manage hotline | Setup hotline | As BA I can add a Greeting message for CA to start the call |  | Todo | 8.00 | Sprint 11 Tipalti enhancements (withdraw full balance or certain amount), switching to new API, Purchase numbers flow, testing | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable Events module for hotline |  | Todo | 2.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage hotline | Setup hotline | As BA I can create a hotline before I buy a phone number |  | Todo | 8.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable Media module (for timetables) for hotline |  | Todo | 2.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable module Places |  | Todo | 2.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable module Stuff members |  | Todo | 2.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable module FAQ for hotline |  | Todo | 2.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage hotline | Setup hotline | As BA I can see how much Hotline costs me depending on requirements I set (frontend only) |  | Todo | 5.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage hotline | Setup hotline | As BA I can buy phone number for a hotline (basic version) |  | Todo | 8.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable module Product catalogue for a hotline |  | Todo | 6.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can link a product with to hotline |  | Todo | 12.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can view matched CA for my hotline |  | Todo | 25.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can enable/disable module Appointment for a hotline |  | Todo | 12.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can set not lower or not higher level of language |  | Todo | 8.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can set not lower or not higher level of degree |  | Todo | 8.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can set the Industries |  | Todo | 6.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage hotline | Setup hotline | As BA I can set the number for the hotline |  | Todo | 12.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage hotline | Setup hotline | As BA option so set the type of the call (Service, Sale...) |  | Todo | 4.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Lawyer Jack
Manage hotline | Setup hotline | As BA I can set welcome music from available list for queues |  | Todo | 16.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Lawyer Jack
Manage hotline | Manage calls | As BA I can view calls list and play recordings |  | Todo | 25.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Lawyer Jack
Manage billing | Setup billing details | Top up account (one off) with Payoneer |  | Todo |  | Unscheduled | Lawyer Jack
Manage billing | Setup billing details | Set auto top up account |  | Todo |  | Unscheduled | Lawyer Jack
Manage billing | Setup billing details | As BA with 0 balance I can't proceed running the hotline and get an email notification about running out of money |  | Todo |  | Unscheduled | Lawyer Jack
Manage billing | Setup billing details | As BA I can deposit money on my account using Tranzilla | Including. cahier calculator with PhoneDo fees | Todo | 70.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Lawyer Jack
Manage billing | View spendings | As BA I can view how much each call cost me (and details breakdown) |  | Todo | 24.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Lawyer Jack
Manage billing | View spendings | As BA I can view all transactions (deposit and charges) |  | Todo | 16.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | As BA I can view taken message from customer in lead details |  | Todo | 8.00 | Sprint 11 Tipalti enhancements (withdraw full balance or certain amount), switching to new API, Purchase numbers flow, testing | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | As BA I can view CA's notes to me (Agent notes to Business) in lead details |  | Todo | 8.00 | Sprint 11 Tipalti enhancements (withdraw full balance or certain amount), switching to new API, Purchase numbers flow, testing | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | As BA I can view customers registered for Events |  | Todo | 20.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | As BA I can view appointments set by CA (link in Lead to Calendar section |  | Todo | 16.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | As BA I can view Customers' answers for my Surveys |  | Todo | 16.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | View own leads grid |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Lawyer Jack
Manage leads and customers | View list of leads and leads' details | View lead details |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Lawyer Jack
Manage leads and customers | Evaluate leads (rating, feeback, bonus, favourite) | As BA I can rate the call by 3 parameters (stars) |  | Todo | 30.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Lawyer Jack
Manage leads and customers | Evaluate leads (rating, feeback, bonus, favourite) | As BA I can provide text feedback to a CA for a lead |  | Todo | 16.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Lawyer Jack
Manage leads and customers | Evaluate leads (rating, feeback, bonus, favourite) | As BA I can send bonus to a CA for a lead |  | Todo | 30.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Lawyer Jack
Manage leads and customers | Evaluate leads (rating, feeback, bonus, favourite) | As BA I can add a CA to favourites |  | Todo | 12.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Lawyer Jack
Manage leads and customers | View list of own customers (grid) | View own customers grid |  | Done | 4.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Lawyer Jack
Manage leads and customers | View list of own customers (grid) | View own customer details |  | Done | 4.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Lawyer Jack
Manage own account | Authorization | As Partner I can signup with PhoneDo (following onboarding screens) |  | Todo | 14.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Partner
Manage own account | Authorization | As Partner after registration I can get my partner code for further customers affiliating |  | Todo | 24.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Partner
Manage own account | Authorization | As Service provider I can signup (onboarding screens) |  | Todo | 16.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Peter
Manage own account | Authorization | As Service provider I can signup (no onboarding version) |  | Todo | 8.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Peter
Manage users | Add/update, remove users | As admin I can set approved/not approved status for users |  | Todo | 4.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Admin
Manage users | Add/update, remove users | As admin I can set user Early adoptor to be able to singin (instead of just Apology page) |  | Todo | 6.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Admin
Manage users | Add/update, remove users | Option to set industry for a BA |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage users | Add/update, remove users | Option to set Industries for Call agents |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage users | Add/update, remove users | Option to set Languages and levels for CA |  | Done | 4.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage users | Add/update, remove users | Option to set Languages and levels for BA |  | Done | 4.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage users | Add/update, remove users | View users grid |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage users | Add/update, remove users | Add Business account | Username Company name Password | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage users | Add/update, remove users | Option to add a Call agent account | Given name Family name Telephone Language + Level × Add a new item Password | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage users | Manage scripts | Open the section with and view the list of BA scripts (grid) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage users | Manage scripts | Option to update scripts (Title, text) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage preferences | Manage Industries | View industries grid |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage preferences | Manage Industries | Add new/update industry |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage preferences | Manage Services | As Admin I can add and edit services labels |  | Todo | 6.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Admin
Manage numbers and calls | Allocate numbers | View available numbers (grid) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage numbers and calls | Allocate numbers | View allocated numbers (grid) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage numbers and calls | Allocate numbers | Select available number and allocate to a selected BA |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | Admin
Manage numbers and calls | View calls and listen to recordings | View calls grid | Including Enswitch integration for it | Done | 8.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage numbers and calls | View calls and listen to recordings | Listen to call recordings | Real-time sync calls | Done | 6.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage numbers and calls | View all customers | View all customers grid |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage numbers and calls | View all customers | View any customer details |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage translations | Add a language and translatons | As Admin (or Contributor) I can add a new language and manage translations for it |  | Todo | 4.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Admin
Manage billing | View and manage billing mechanism | As admin I can update billing criteria |  | Todo | 16.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Admin
Manage billing | Manage users' billing | As admin I can view call costs and earnings |  | Todo | 8.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Admin
Manage billing | Manage users' billing | As admin I can create or remove transactions |  | Todo | 6.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Admin
Manage billing | Manage users' billing | View transactions grid |  | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
Manage billing | Manage users' billing | Add a new transaction for a selected user | Fileds: Amount Account Notes | Done | 2.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Admin
API for authentication | Register call agent | Business account signup api (with auto-setup personal queue) |  | Todo | 10.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | Business account login api |  | Todo | 2.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | Hotline api exposing (DTO, validation, serialization, e.t.c) |  | Todo | 20.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | Purchased numbers API exposing |  | Todo | 15.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | Queue api exposing |  | Todo | 12.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | Qeueu music api exposing |  | Todo | 5.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | Improve script api (priroity) |  | Todo | 2.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Register call agent | API method to register a call agent user in the system |  | Done | 3.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | API
API for authentication | Register call agent | API method to sign in a call agent |  | Done | 3.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | API
API for authentication | Register call agent | API method industry set, update (permissions) |  | Done | 3.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | API
API for authentication | Register call agent | API method to set Languages and levels for CA (permissions) |  | Done | 3.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | API
API for authentication | Register call agent | API method to get allocated numbers (list) |  | Done |  | Sprint 1 Setup project, Basic entities, API methods, Admin panel | API
API for authentication | Manage push notif. |  |  | Todo |  | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Manage push notif. | Improve PUSH strategies: auto-hangup call message |  | Todo | 8.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | API
API for authentication | Manage push notif. | Setup push notification system |  | Done | 4.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | API
API for Translations | Integration to manage translations | Setup translations architecture |  | Todo | 40.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | API
API for Translations | Integration to manage translations | Setup API for Integration with Poeditor |  | Todo | 25.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | API
Manage own account | Open the app | As CA by default I get basic settings (lang, education, industry) |  | Todo | 6.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Sassy
Manage own account | Open the app | Open installed app | Setup mobile app project for that | Done | 20.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage own account | Sign up | As CA I can signup on the web as well (onboarding screens+apology page) |  | Todo | 40.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Sassy
Manage own account | Sign up | As CA when registering I can select my country and get the country phone code (prefix) |  | Todo | 12.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Sassy
Manage own account | Sign up | As CA I can verify my phone number with SMS code and proceed with registration |  | Todo | 30.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Sassy
Manage own account | Sign up | Sign up in the app (CA) |  | Done | 4.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage own account | Sign in | As CA I can sign out (app) |  | Todo | 2.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage own account | Sign in | Sign in in the app (CA) |  | Done | 3.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage own account | Manage account preferences | As СA I can switch application language |  | Todo | 12.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Sassy
Manage own account | Manage account preferences | As CA I can add my billing details for getting paid |  | Todo | 4.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Sassy
Manage own account | Manage account preferences | As CA I can set myself education degree (in the app) | BA Master's degree Dr. Professor | Todo | 8.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage own account | Manage account preferences | As CA I can set myself Industries (in the app) |  | Todo | 8.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage own account | Manage account preferences | As CA I can set Languages and levels (app) |  | Todo | 8.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage own account | Manage account preferences | Option to set Languages and level for himself (web) |  | Done | 12.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage own account | Manage account preferences | Option to set Industries for himself (web) |  | Done | 12.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage own account | Getting support | As CA I can use Zendesk chat support to get help from PhoneDo support |  | Todo | 10.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy
Manage calls, scripts, leads | Receive calls | Option to decline call (when in the app) |  | Todo |  | Unscheduled | Sassy
Manage calls, scripts, leads | Receive calls | As CA being set as favourite by BA I receive push notification in the first "wave" |  | Todo | 24.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy
Manage calls, scripts, leads | Receive calls | Option to receive push notif. on an inc. call if lang. and industries match (app) | Process the incoming call - put in the queue Backend checks the rules Send push | Done | 30.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage calls, scripts, leads | Receive calls | Option to accept a call (when in the app) | The first CA accepts, others won't be able to get the call anymore | Done | 12.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage calls, scripts, leads | Receive calls | Option to see the call has been answered by another CA |  | Done | 6.00 | Sprint 2 Call agent receives push and gets the call, language and industry match | Sassy
Manage calls, scripts, leads | Getting acquainted with Hotlines matching with my Preferences | As CA I can view Hotlines that match with my criteria to get acquainted with the scripts |  | Todo | 18.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Sassy
Manage calls, scripts, leads | Get company's details | As CA I can view the main details about the hotline |  | Todo | 8.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Sassy
Manage calls, scripts, leads | Get company's details | As CA I can view company's details on an incoming call |  | Todo | 6.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage calls, scripts, leads | Get script | As CA I can view a greeting message on an incoming call |  | Todo | 10.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy
Manage calls, scripts, leads | Get script | As CA I can view Survey script and fill it with customer's answers |  | Todo | 32.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Sassy
Manage calls, scripts, leads | Get script | As CA I can get list of Available Scripts once got an incoming call |  | Todo | 12.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage calls, scripts, leads | Get script | As CA I can select from available scripts and view text |  | Todo | 10.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage calls, scripts, leads | Use modules | As CA I can forward the call to a Stuff member |  | Todo |  | Unscheduled | Sassy
Manage calls, scripts, leads | Use modules | As CA I can view Media added by BA |  | Todo | 16.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Sassy
Manage calls, scripts, leads | Use modules | As CA I can view event details and register customers filling the form |  | Todo | 36.00 | Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system | Sassy
Manage calls, scripts, leads | Use modules | As CA I can view Stuff members cards |  | Todo | 16.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Sassy
Manage calls, scripts, leads | Use modules | As CA I can view Places and filter by existing types |  | Todo | 25.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Sassy
Manage calls, scripts, leads | Use modules | As CA I can view Hotline's FAQ added by BA |  | Todo | 16.00 | Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch | Sassy
Manage calls, scripts, leads | Use modules | As CA I can view products and their details to communicate them to customers |  | Todo | 25.00 | Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 | Sassy
Manage calls, scripts, leads | Fill the leads form with the info taken from customer | As CA during call I can take a message from Caller (text) and save in lead details |  | Todo | 12.00 | Sprint 11 Tipalti enhancements (withdraw full balance or certain amount), switching to new API, Purchase numbers flow, testing | Sassy
Manage calls, scripts, leads | Fill the leads form with the info taken from customer | As CA during call I can enter Purpose of the call in lead details |  | Todo | 10.00 | Sprint 11 Tipalti enhancements (withdraw full balance or certain amount), switching to new API, Purchase numbers flow, testing | Sassy
Manage calls, scripts, leads | Fill the leads form with the info taken from customer | As CA I can view BA calendar with available time slots |  | Todo | 25.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Sassy
Manage calls, scripts, leads | Fill the leads form with the info taken from customer | As CA I can set an appointment for a Customer in BA calendar |  | Todo | 16.00 | Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 | Sassy
Manage calls, scripts, leads | Fill the leads form with the info taken from customer | As CA I can type the info and save (in lead) on incoming call |  | Todo | 12.00 | Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details | Sassy
Manage calls, scripts, leads | View ratings from BA | As CA I can view stars rating from BA for a lead (if provided) |  | Todo | 10.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Sassy
Manage calls, scripts, leads | View ratings from BA | As CA I can view Feedback provided by BA in a lead |  | Todo | 12.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Sassy
Manage calls, scripts, leads | View ratings from BA | As CA I can view bonus sent by BA in my leads |  | Todo | 12.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Sassy
Manage calls, scripts, leads | View ratings from BA | As CA I can see I was added to favourites after some lead |  | Todo | 10.00 | Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup | Sassy
Manage calls, scripts, leads | Manage call settings | As CA I can switch audio to be speaker or earpiece |  | Todo | 12.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy
Manage calls, scripts, leads | Manage call settings | As CA I can put a call on hold |  | Todo | 16.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy
Manage billing | View earnings | As CA I can see how much I earned on each call |  | Todo | 12.00 | Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app | Sassy
Manage billing | Withdraw money | As CA I can setup my billing details with Tipalti |  | Todo | 25.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy
Manage billing | Withdraw money | As CA I can request a withdrawal (Tipalti) |  | Todo | 42.00 | Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs | Sassy

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Unscheduled |  |  |  | False | False
Sprint 11 Tipalti enhancements (withdraw full balance or certain amount), switching to new API, Purchase numbers flow, testing |  |  |  | False | False
Sprint 10 Business account can top up balance - one off (Tranzilla), SIP solution version for iOS, audio output switch (speaker/dynamic), Tipalti for payouts for CAs |  |  |  | False | False
Sprint 9 Call agent rating system. Adding feedback, provide bonus, make favourite. SIP solution version for iOS basic setup |  |  |  | False | False
Sprint 8 Service provider, Partner roles, onboarding for them. Billing (money, rates, calculation fo CA and BA), SIP solution basic setup (Android), API for BA app |  |  |  | False | False
Sprint 7 BA onboarding flow+Aplology page, Events module, media (for timetables) modules, Apologies page to register CA interested in the system |  |  |  | False | False
Sprint 6 BA onboarding flow, Modules Places, Stuff members, Recordings from Enswitch |  |  |  | False | False
Sprint 5 Adding Catalog module, Phone verification for CA on signup (sms), Translations (RU, EN) 25.04-11.05 |  |  |  | False | False
Sprint 4 Adding type of script Survey, module Appointments, more preferences for CA, BA (skills, interests) 10.04-24.04 |  |  |  | False | False
Sprint 3 BA creates hotline, add scripts, Call agent gets simple scripts, fills lead details |  |  |  | False | False
Sprint 2 Call agent receives push and gets the call, language and industry match |  |  |  | False | False
Sprint 1 Setup project, Basic entities, API methods, Admin panel |  |  |  | False | False

## Personas
Persona | Group | Details | Picture
Sassy | Call agents |  | 21
API | System |  | 32
Partner | Business partner (affiliate) |  | 18
Admin | PhoneDo |  | 34
Lawyer Jack | Business Account |  | 9
Peter |  |  | 25